## ProductBacklog
PRODUCT BACKLOG
Batch 2018-2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | User | Open web portal | I can access the Venue Booking System | 1 | Gargi Kaushik | 2018-09-22
1 | SB1/US2 | User | Register myself as user | I am authorized to access the application | 1 | Gargi Kaushik | 2018-09-22
1 | SB1/US3 | User | Complete my registration | I can receive a confirmation/verification mail | 1 | Gargi Kaushik | 2018-09-22
1 | SB1/US4 | User | Verify my E-Mail | I can complete my profile | 1 | Gargi Kaushik | 2018-09-22
1 | SB1/US5 | User | Login into the system using Mail Id & Password | I can view/update my profile | 1 | Gargi Kaushik | 2018-09-22
1 | SB1/US6 | User | See the available venues | I can select my preferred choice | 2 | Gargi Kaushik | 2018-09-22
1 | SB1/US7 | User | Enter my location | I can view the available venues to be booked | 2 | Gargi Kaushik | 2018-09-29
1 | SB1/US8 | User | View the venues available | I can decide which venue to book | 2 | Gargi Kaushik | 2018-09-29
1 | SB1/US9 | User | Select the venue | I can confirm my reservation | 3 | Gargi Kaushik | 2018-09-29
1 | SB1/US10 | User | View all the venues available at the location | I can decide which venue to book | 3 | Gargi Kaushik | 2018-09-29
1 | SB1/US11 | User | Check the selected venue details | I can assure my booking | 3 | Gargi Kaushik | 2018-10-02
1 | SB1/US12 | User | Book the venue | I can send booking details to owner for confirmation | 3 | Gargi Kaushik | 2018-10-02
1 | SB1/US13 | User | Provide all the necessary information | I can confirm my booking | 3 | Gargi Kaushik | 2018-10-02
1 | SB1/US14 | User | Confirm my venue booking | I can get my venue reserved for that day | 4 | Gargi Kaushik | 2018-10-02
1 | SB1/US15 | User | Save the booking details as PDF | I can have confirmation of my booking | 4 | Gargi Kaushik | 2018-10-02
1 | SB1/US16 | User | Give feedback/suggestions | I can see the further improvements in the webpage | 4 | Gargi Kaushik | 2018-10-09
1 | SB1/US17 | User | Sign out of the system | No one can access my user account | 4 | Gargi Kaushik | 2018-10-09
2 | SB2/US1 | Owner | Open web portal | I can access the Venue Booking System | 1 | Gargi Kaushik | 2018-10-09
2 | SB2/US2 | Owner | Register myself as owner | I am authorized to access the application | 1 | Gargi Kaushik | 2018-10-09
2 | SB2/US3 | Owner | Complete my registration | I can receive a confirmation/verification mail | 1 | Gargi Kaushik | 2018-10-16
2 | SB2/US4 | Owner | Verify my E-Mail | I can complete my profile | 1 | Gargi Kaushik | 2018-10-16
2 | SB2/US5 | Owner | Login into the system using Mail Id & Password | I can view/update my profile | 2 | Gargi Kaushik | 2018-10-16
2 | SB2/US6 | Owner | Add my venues available for booking | I can receive bookings from users | 2 | Gargi Kaushik | 2018-10-16
2 | SB2/US7 | Owner | Add venue details | I can provide information to the users | 2 | Konica Chakrabortty | 2018-10-16
2 | SB2/US8 | Owner | Insert venue price, loactions, timing | I can receive bookings from users | 2 | Konica Chakrabortty | 2018-10-23
2 | SB2/US9 | Owner | Add my venues available for booking | I can receive bookings from users | 3 | Konica Chakrabortty | 2018-10-23
2 | SB2/US10 | Owner | Check the bookings statistics | I can adjust the venue timing according to it | 3 | Konica Chakrabortty | 2018-10-23
2 | SB2/US11 | Owner | Send confirmation to the users | I can deny other request for same slot available | 3 | Konica Chakrabortty | 2018-10-23
2 | SB2/US12 | Owner | Confirm the payment method | I can confirm their reservation | 4 | Konica Chakrabortty | 2018-10-30
2 | SB2/US13 | Owner | Add other venue (If applicable) | I can continue receiving booking | 4 | Konica Chakrabortty | 2018-10-30
2 | SB2/US14 | Owner | View the feedback/suggestions | I can improve my service | 4 | Konica Chakrabortty | 2018-10-30
2 | SB2/US15 | Owner | Sign out of the system | No one can access my user account | 4 | Konica Chakrabortty | 2018-10-30
3 | SB3/US1 | Admin | Open web portal | I can access the Venue Booking System | 3 | Konica Chakrabortty | 2018-10-07
4 | SB3/US2 | Admin | Login into the system using Mail Id & Password | I can authorize my admin access | 4 | Konica Chakrabortty | 2018-10-07
5 | SB3/US3 | Admin | View all the users | I can verify his/her profile | 4 | Konica Chakrabortty | 2018-10-07
6 | SB3/US4 | Admin | View all the users booking | I can update the information on dashboard | 4 | Konica Chakrabortty | 2018-10-07
7 | SB3/US5 | Admin | View all the confirmed booking | I can update the information on dashboard | 4 | Konica Chakrabortty | 2018-10-07
8 | SB3/US6 | Admin | View all the users booking | I can update the information | 4 | Konica Chakrabortty | 2018-10-14
9 | SB3/US7 | Admin | Delete malicious user profiles | I can have user data updated | 5 | Konica Chakrabortty | 2018-10-14
10 | SB3/US8 | Admin | View all the owners | I can verify his/her profile | 5 | Konica Chakrabortty | 2018-10-14
11 | SB3/US9 | Admin | Check the bookings of each owner | I can update the information on dashboard | 5 | Konica Chakrabortty | 2018-10-14
12 | SB3/US10 | Admin | Confirm booking with owner | I can update the information on dashboard | 5 | Konica Chakrabortty | 2018-10-14
13 | SB3/US11 | Admin | Delete malicious owner profiles | I can have owner data updated | 6 | Konica Chakrabortty | 2018-10-21
14 | SB3/US12 | Admin | View all the available venues | I can display available venues in user dashboard | 6 | Konica Chakrabortty | 2018-10-21
15 | SB3/US13 | Admin | Check the bookings statistics | I can send booking information to owner | 6 | Konica Chakrabortty | 2018-10-21
16 | SB3/US14 | Admin | View the feedback/suggestions | I can improve my service | 6 | Konica Chakrabortty | 2018-10-21
17 | SB3/US15 | Admin | Sign out of the system | No one can access my user account | 6 | Konica Chakrabortty | 2018-10-21

## SprintBacklog1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - VENUE BOOKING SYSTEM
SB1/US1 | Open web portal | SB1/D1/T1 | Design the GUI | Gargi Kaushik | In progress | 2018-09-22
|  | SB1/D1/T2 | Coding | Gargi Kaushik | In progress | 2018-09-22
|  | SB1/D1/T3 | Connect with Database | Gargi Kaushik | In progress | 2018-09-22
SB1/US2 | Register myself as user | SB1/D2/T4 | Design the GUI | Gargi Kaushik | Not Started | 2018-09-22
|  | SB1/D2/T5 | Coding | Gargi Kaushik | Not Started | 2018-09-22
|  | SB1/D2/T6 | Connect with Database | Gargi Kaushik | Not Started | 2018-09-22
SB1/US3 | Complete my registration | SB1/D3/T7 | Design the GUI | Gargi Kaushik | Not Started | 2018-09-29
|  | SB1/D3/T8 | Coding | Gargi Kaushik | Not Started | 2018-09-29
|  | SB1/D3/T9 | Connect with Database | Gargi Kaushik | Not Started | 2018-09-29
SB1/US4 | Verify my E-Mail | SB1/D4/T10 | Design the GUI | Gargi Kaushik | Not Started | 2018-09-29
|  | SB1/D4/T11 | Coding | Gargi Kaushik | Not Started | 2018-10-02
|  | SB1/D4/T12 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-02
SB1/US5 | Login into the system using Mail Id & Password | SB1/D5/T13 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-02
|  | SB1/D5/T14 | Coding | Gargi Kaushik | Not Started | 2018-10-02
|  | SB1/D5/T15 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-02
SB1/US6 | See the available venues | SB1/D6/T16 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-09
|  | SB1/D6/T17 | Coding | Gargi Kaushik | Not Started | 2018-10-09
|  | SB1/D6/T18 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-09
SB1/US7 | Enter my location | SB1/D7/T19 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-09
|  | SB1/D7/T20 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB1/D7/T21 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB1/US8 | View the venues available | SB1/D8/22 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB1/D8/T23 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB1/D8/T24 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB1/US9 | Select the venue | SB1/D9/T25 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB1/D9/T26 | Coding | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB1/D9/T27 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-23
SB1/US10 | View all the venues available at the location | SB1/D10/T28 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB1/D10/T29 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB1/D10/T30 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-30
SB1/US11 | Check the selected venue details | SB1/D11/T31 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB1/D11/T32 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB1/D11/T33 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-07
SB1/US12 | Book the venue | SB1/D12/T34 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-07
|  | SB1/D12/T35 | Coding | Konica Chakrabortty | Not Started | 2018-10-07
|  | SB1/D12/T36 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-07
SB1/US13 | Provide all the necessary information | SB1/D13/T37 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-07
|  | SB1/D13/T38 | Coding | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB1/D13/T39 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-14
SB1/US14 | Confirm my venue booking | SB1/D14/T40 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB1/D14/T41 | Coding | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB1/D14/T42 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-14
SB1/US15 | Save the booking details as PDF | SB1/D15/T43 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB1/D15/T44 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB1/D15/T45 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB1/US16 | Give feedback/suggestions | SB1/D16/T46 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB1/D16/T47 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB1/D16/T48 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB1/US17 | Sign out of the system | SB1/D17/T49 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-28
|  | SB1/D17/T50 | Coding | Konica Chakrabortty | Not Started | 2018-10-28
|  | SB1/D17/T51 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-28

## SB HOURS 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-22 | 51 | 51
2018-10-21 | 0 | 51
Days

## SprintBacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - VENUE BOOKING SYSTEM
SB2/US1 | Open web portal | SB2/D1/T1 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-09
|  | SB2/D1/T2 | Coding | Gargi Kaushik | Not Started | 2018-10-09
|  | SB2/D1/T3 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-09
SB2/US2 | Register myself as owner | SB2/D2/T4 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-09
|  | SB2/D2/T5 | Coding | Gargi Kaushik | Not Started | 2018-10-09
|  | SB2/D2/T6 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-09
SB2/US3 | Complete my registration | SB2/D3/T7 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D3/T8 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D3/T9 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB2/US4 | Verify my E-Mail | SB2/D4/T10 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D4/T11 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D4/T12 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB2/US5 | Login into the system using Mail Id & Password | SB2/D5/T13 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D5/T14 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D5/T15 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB2/US6 | Add my venues available for booking | SB2/D6/T16 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D6/T17 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D6/T18 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB2/US7 | Add venue details | SB2/D7/T19 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D7/T20 | Coding | Gargi Kaushik | Not Started | 2018-10-16
|  | SB2/D7/T21 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-16
SB2/US8 | Insert venue price, loactions, timing | SB2/D8/T22 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D8/T23 | Coding | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D8/T24 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-23
SB2/US9 | Add my venues available for booking | SB2/D9/T25 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D9/T26 | Coding | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D9/T27 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-23
SB2/US10 | Check the bookings statistics | SB2/D10/T28 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D10/T29 | Coding | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D10/T30 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-23
SB2/US11 | Send confirmation to the users | SB2/D11/T31 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D11/T32 | Coding | Konica Chakrabortty | Not Started | 2018-10-23
|  | SB2/D11/T33 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-23
SB2/US12 | Confirm the payment method | SB2/D12/T34 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D12/T35 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D12/T36 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-30
SB2/US13 | Add other venue (If applicable) | SB2/D13/T37 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D13/T38 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D13/T39 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-30
SB2/US14 | View the feedback/suggestions | SB2/D14/T40 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D14/T41 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D14/T42 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-30
SB2/US15 | Sign out of the system | SB2/D15/T43 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D15/T44 | Coding | Konica Chakrabortty | Not Started | 2018-10-30
|  | SB2/D15/T45 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-30

## SB HOURS 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-09 | 45 | 45
2018-10-30 | 0 | 45
Days

## SprintBacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - VENUE BOOKING SYSTEM
SB3/US1 | Open web portal | SB3/D1/T1 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D1/T2 | Coding | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D1/T3 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-07
SB3/US2 | Login into the system using Mail Id & Password | SB3/D2/T4 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D2/T5 | Coding | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D2/T6 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-07
SB3/US3 | View all the users | SB3/D3/T7 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D3/T8 | Coding | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D3/T9 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-07
SB3/US4 | View all the users booking | SB3/D4/T10 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D4/T11 | Coding | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D4/T12 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-07
SB3/US5 | View all the confirmed booking | SB3/D5/T13 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D5/T14 | Coding | Gargi Kaushik | Not Started | 2018-10-07
|  | SB3/D5/T15 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-07
SB3/US6 | View all the users booking | SB3/D6/T16 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-14
|  | SB3/D6/T17 | Coding | Gargi Kaushik | Not Started | 2018-10-14
|  | SB3/D6/T18 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-14
SB3/US7 | Delete malicious user profiles | SB3/D7/T19 | Design the GUI | Gargi Kaushik | Not Started | 2018-10-14
|  | SB3/D7/T20 | Coding | Gargi Kaushik | Not Started | 2018-10-14
|  | SB3/D7/T21 | Connect with Database | Gargi Kaushik | Not Started | 2018-10-14
SB3/US8 | View all the owners | SB3/D8/T22 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D8/T23 | Coding | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D8/T24 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-14
SB3/US9 | Check the bookings of each owner | SB3/D9/T25 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D9/T26 | Coding | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D9/T27 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-14
SB3/US10 | Confirm booking with owner | SB3/D10/T28 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D10/T29 | Coding | Konica Chakrabortty | Not Started | 2018-10-14
|  | SB3/D10/T30 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-14
SB3/US11 | Delete malicious owner profiles | SB3/D11/T31 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D11/T32 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D11/T33 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB3/US12 | View all the available venues | SB3/D12/T34 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D12/T35 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D12/T36 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB3/US13 | Check the bookings statistics | SB3/D13/T37 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D13/T38 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D13/T39 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB3/US14 | View the feedback/suggestions | SB3/D14/T40 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D14/T41 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D14/T42 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21
SB3/US15 | Sign out of the system | SB3/D15/T43 | Design the GUI | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D15/T44 | Coding | Konica Chakrabortty | Not Started | 2018-10-21
|  | SB3/D15/T45 | Connect with Database | Konica Chakrabortty | Not Started | 2018-10-21

## SB HOURS 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch03
Spring Backlog 03 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-07 | 45 | 45
2018-10-21 | 0 | 45
Days