## ProductBacklog
PRODUCT BACKLOG
Batch 2018-2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | User | Register myself as user | I can receive a confirmation/verification mail | 1 |  | 2018-09-12
1 | SB1/US2 | User | Receive a confirmation mail | I can access the Venue Booking System | 1 |  | 2018-09-12
1 | SB1/US3 | User | Login into the system using Mail Id & Password | I can view/update my profile | 2 |  | 2018-09-12
1 | SB1/US4 | User | Enter my location | I can view the available venues to be booked | 1 |  | 2018-09-12
1 | SB1/US5 | User | View the venues available | I can decide which venue to book | 2 |  | 2018-09-18
1 | SB1/US6 | User | Book the venue | I can send booking details to owner for confirmation | 3 |  | 2018-09-18
1 | SB1/US7 | User | Save the booking details as PDF | I can have confirmation of my booking | 3 |  | 2018-09-18
1 | SB1/US8 | User | Give feedback/suggestions | I can see the further improvements in the webpage | 4 |  | 2018-09-18
2 | SB2/US1 | Owner | Register myself as owner | I can receive a confirmation/verification mail | 4 |  | 2018-09-18
2 | SB2/US2 | Owner | Receive a confirmation mail | I can access the Venue Booking System | 4 |  | 2018-09-18
2 | SB2/US3 | Owner | Login into the system using Mail Id & Password | I can view/update my profile | 1 |  | 2018-10-02
2 | SB2/US4 | Owner | Add my venues available for booking | I can receive bookings from users | 1 |  | 2018-10-02
2 | SB2/US5 | Owner | Check the bookings statistics | I can confirm bookings for users | 2 |  | 2018-10-02
2 | SB2/US6 | Owner | View the feedback/suggestions | I can improve my service | 3 |  | 2018-10-02
3 | SB3/US1 | Admin | View all the users | I can verify his/her profile | 3 |  | 2018-10-07
3 | SB3/US2 | Admin | Delete malicious user profiles | I can have user data updated | 4 |  | 2018-10-07
3 | SB3/US3 | Admin | View all the owners | I can verify his/her profile | 4 |  | 2018-10-07
3 | SB3/US4 | Admin | Delete malicious owner profiles | I can have owner data updated | 4 |  | 2018-10-07
3 | SB3/US5 | Admin | View all the available venues | I can display available venues in user dashboard | 4 |  | 2018-10-07
3 | SB3/US6 | Admin | Check the bookings statistics | I can send booking information to owner | 4 |  | 2018-10-07
3 | SB3/US7 | Admin | Verify the booking | I can send confirmation to user | 4 |  | 2018-10-07
3 | SB3/US8 | Admin | View the feedback/suggestions | I can improve my service | 4 |  | 2018-10-07

## SprintBacklog1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - VENUE BOOKING SYSTEM
SB1/US1 | Register myself as user | SB1/D1/T1 | Design the GUI | Gargi | In progress | 2018-09-15
|  | SB1/D1/T2 | Coding | Gargi | In progress | 2018-09-15
|  | SB1/D1/T3 | Connect with Database | Gargi | In progress | 2018-09-15
SB1/US2 | Receive a confirmation mail | SB1/D2/T1 | Design the GUI | Gargi | Not Started | 2018-09-15
|  | SB1/D2/T2 | Coding | Gargi | Not Started | 2018-09-15
|  | SB1/D2/T3 | Connect with Database | Gargi | Not Started | 2018-09-15
SB1/US3 | Login into the system using Mail Id & Password | SB1/D3/T1 | Design the GUI | Gargi | Not Started | 2018-09-18
|  | SB1/D3/T2 | Coding | Gargi | Not Started | 2018-09-18
|  | SB1/D3/T3 | Connect with Database | Gargi | Not Started | 2018-09-18
SB1/US4 | Enter my location | SB1/D4/T1 | Design the GUI | Gargi | Not Started | 2018-09-18
|  | SB1/D4/T2 | Coding | Gargi | Not Started | 2018-09-18
|  | SB1/D4/T3 | Connect with Database | Gargi | Not Started | 2018-09-18
SB1/US5 | View the venues available | SB1/D5/T1 | Design the GUI | Konica | Not Started | 2018-09-18
|  | SB1/D5/T2 | Coding | Konica | Not Started | 2018-09-18
|  | SB1/D5/T3 | Connect with Database | Konica | Not Started | 2018-09-18
SB1/US6 | Book the venue | SB1/D6/T1 | Design the GUI | Konica | Not Started | 2018-09-18
|  | SB1/D6/T2 | Coding | Konica | Not Started | 2018-09-18
|  | SB1/D6/T3 | Connect with Database | Konica | Not Started | 2018-09-18
SB1/US7 | Reached the destination | SB1/D7/T1 | Design the GUI | Konica | Not Started | 2018-09-18
|  | SB1/D7/T2 | Coding | Konica | Not Started | 2018-09-18
|  | SB1/D7/T3 | Connect with Database | Konica | Not Started | 2018-09-18
SB1/US8 | Save the booking details as PDF | SB1/D8/T1 | Design the GUI | Konica | Not Started | 2018-09-18
|  | SB1/D8/T2 | Coding | Konica | Not Started | 2018-09-18
|  | SB1/D8/T3 | Connect with Database | Konica | Not Started | 2018-09-18
SB1/US9 | Give feedback/suggestions | SB1/D9/T1 | Design the GUI | Konica | Not Started | 2018-09-18
|  | SB1/D9/T2 | Coding | Konica | Not Started | 2018-09-18
|  | SB1/D9/T3 | Connect with Database | Konica | Not Started | 2018-09-18

## SB HOURS 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-12 | 24 | 24
2018-09-18 | 0 | 24
Days

## SprintBacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - VENUE BOOKING SYSTEM
SB2/US1 | Register myself as owner | SB2/D1/T1 | Design the GUI | Gargi | Not Started | 2018-10-02
|  | SB2/D1/T2 | Coding | Gargi | Not Started | 2018-10-02
|  | SB2/D1/T3 | Connect with Database | Gargi | Not Started | 2018-10-02
SB2/US2 | Receive a confirmation mail | SB2/D2/T1 | Design the GUI | Gargi | Not Started | 2018-10-02
|  | SB2/D2/T2 | Coding | Gargi | Not Started | 2018-10-02
|  | SB2/D2/T3 | Connect with Database | Gargi | Not Started | 2018-10-02
SB2/US3 | Login into the system using Mail Id & Password | SB2/D3/T1 | Design the GUI | Gargi | Not Started | 2018-10-02
|  | SB2/D3/T2 | Coding | Gargi | Not Started | 2018-10-02
|  | SB2/D3/T3 | Connect with Database | Gargi | Not Started | 2018-10-02
SB2/US4 | Add my venues available for booking | SB2/D4/T1 | Design the GUI | Gargi | Not Started | 2018-10-02
|  | SB2/D4/T2 | Coding | Konica | Not Started | 2018-10-02
|  | SB2/D4/T3 | Connect with Database | Konica | Not Started | 2018-10-02
SB2/US5 | Check the bookings statistics | SB2/D5/T1 | Design the GUI | Konica | Not Started | 2018-10-02
|  | SB2/D5/T2 | Coding | Konica | Not Started | 2018-10-02
|  | SB2/D5/T3 | Connect with Database | Konica | Not Started | 2018-10-02
SB2/US6 | See the feedback/suggestions | SB2/D6/T1 | Design the GUI | Konica | Not Started | 2018-10-02
|  | SB2/D6/T2 | Coding | Konica | Not Started | 2018-10-02
|  | SB2/D6/T3 | Connect with Database | Konica | Not Started | 2018-10-02
SB2/US7 | Update the system | SB2/D7/T1 | Design the GUI | Konica | Not Started | 2018-10-07
|  | SB2/D7/T2 | Coding | Konica | Not Started | 2018-10-07
|  | SB2/D7/T3 | Connect with Database | Konica | Not Started | 2018-10-07

## SB HOURS 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-02 | 18 | 18
2018-10-07 | 0 | 18
Days

## SprintBacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - VENUE BOOKING SYSTEM
SB3/US1 | View all the users | SB3/D1/T1 | Design the GUI | Gargi | Not Started | 2018-10-16
|  | SB3/D1/T2 | Coding | Gargi | Not Started | 2018-10-16
|  | SB3/D1/T3 | Connect with Database | Gargi | Not Started | 2018-10-16
SB3/US2 | Delete malicious user profiles | SB3/D2/T1 | Design the GUI | Gargi | Not Started | 2018-10-16
|  | SB3/D2/T2 | Coding | Gargi | Not Started | 2018-10-16
|  | SB3/D2/T3 | Connect with Database | Gargi | Not Started | 2018-10-16
SB3/US3 | View all the owners | SB3/D3/T1 | Design the GUI | Gargi | Not Started | 2018-10-16
|  | SB3/D3/T2 | Coding | Gargi | Not Started | 2018-10-16
|  | SB3/D3/T3 | Connect with Database | Gargi | Not Started | 2018-10-16
SB3/US4 | Delete malicious owner profiles | SB3/D4/T1 | Design the GUI | Gargi | Not Started | 2018-10-16
|  | SB3/D4/T2 | Coding | Gargi | Not Started | 2018-10-16
|  | SB3/D4/T3 | Connect with Database | Konica | Not Started | 2018-10-16
SB3/US5 | View all the available venues | SB3/D5/T1 | Design the GUI | Konica | Not Started | 2018-10-23
|  | SB3/D5/T2 | Coding | Konica | Not Started | 2018-10-23
|  | SB3/D5/T3 | Connect with Database | Konica | Not Started | 2018-10-23
SB3/US6 | Check the bookings statistics | SB3/D6/T1 | Design the GUI | Konica | Not Started | 2018-10-23
|  | SB3/D6/T2 | Coding | Konica | Not Started | 2018-10-23
|  | SB3/D6/T3 | Connect with Database | Konica | Not Started | 2018-10-23
SB3/US7 | Verify the booking | SB3/D7/T1 | Design the GUI | Konica | Not Started | 2018-10-23
|  | SB3/D7/T2 | Coding | Konica | Not Started | 2018-10-23
|  | SB3/D7/T3 | Connect with Database | Konica | Not Started | 2018-10-23
SB3/US8 | View the feedback/suggestions | SB3/D8/T1 | Design the GUI | Konica | Not Started | 2018-10-23
|  | SB3/D8/T2 | Coding | Konica | Not Started | 2018-10-23
|  | SB3/D8/T3 | Connect with Database | Konica | Not Started | 2018-10-23

## SB HOURS 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch03
Spring Backlog 03 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-16 | 24 | 24
2018-10-23 | 0 | 24
Days